## Summary
|  |  | STD information |  |  | Author information
|  |  | STD ID | Test ALL |  | Written by | Kelvin
|  |  | Version of the test sheet |  |  | Writing status | written & reviewed OK
| Version of Orchestra format |  | Project |  |  | Writing date | 2019-06-25
| v20 |  | Test stage
|  |  | Stage category |  |  | Resources required for test
|  |  | Test type |  |  | Estimate preparation duration
|  |  | Verification method (IADT) |  |  | Estimate running duration
|  |  | Applicable location(s) |  |  | Test during TH/NTH
|  |  | Test title |  |  | Number of tester(s)
|  |  | Test objective |  |  | Equipment and quantity
|  |  | Covered requirements |  |  | STD Checksum
| Legends |  | STR information |  |  | Tester information
| To be filled from list |  | System version under test |  |  | Run by | TAT
| Automatically filled |  | Test environment |  |  | Running date | 2019-06-26
| Context step |  | IO schedule version | 20190625
| To be filled by author |  | Instrument calibration certificate |  |  | Resources required for test
| To be filled by tester |  | Allocated location(s) |  |  | Approximate preparation duration
|  |  | Total steps | 159 |  | Approximate running duration
| Language |  | STR results |  |  | Associated defects
| En |  | Total Not Tested | 0
|  |  | Total OK | 33
|  |  | Total OKWC | 0
|  |  | Total NOK | 125
|  |  | Total Not Testable | 0 |  | Comments
|  |  | Total Out Of Scope | 1
|  |  | Test case result | 159
|  |  | Thales Signature |  |  | Customer / External Signature
|  |  | Customer / External Signature |  |  | Customer / External Signature
end | end | end | end | end | end | end | end | end
All sheets
Tester view
Author view
Automation view
Import view
Export view
Set up views
How To view
Custom view

## Views (hidden)
Configuration of the available views
Views
Sheets | Custom | Tester | Author | Import | Export | Views | HowTo | Automation
Summary | Visible | Visible | Visible | Visible | Visible | Visible | Visible | Visible
Views | [5 empty] | Visible
Procedure | Visible | Visible | Visible |  |  |  |  | Visible
User manual |  |  | Visible
defaultValues
How To |  | Visible | Visible |  |  |  | Visible
Language
Automation | [7 empty] | Visible
Export |  |  |  |  | Visible
Import |  |  |  | Visible
ToolVersion
ProcedureVersion |  |  | Visible
Result Matrix |  | Visible

## User manual (hidden)
User Manual
Fields description | View cells comments
Enumeration | Values | meaning | Description
Step State | OK | OK | The observed result is exactly as the expected result
| OKWC | OK with comment | The observed result is almost as the expected result
| NOK | Not OK | The observed result is not as the expected result
| NT | Not Testable | The step description cannot be executed
| OS | Out of scope | The step is not in the scope of the test (e.g. simulated vs real environment)
Context | X | Comment | Use this context to insert comments to the test procudre (NB: for author, not for tester)
| P | Section title | Use this context to insert a section title
Regression thread | Y | Yes | Use this if the thread test regression
| N | No | Use this if the thread not test regression
Writing Status | not written | Not written | The sheet is not written
| in progress | Being written | The sheet is not full written
| written & reviewed OK | Written & reviewed OK | The sheet review is validate
Running Status | not run | not run | The thread was never run
| in progress | being run | The thread is not run completely
| run completed | run completed | The thread was run for an attempt
IADT | I - Inspection | Inspection | The requirement is verified by examination of the product
| A - Analysis | Analysis | The requirement is verified by using model and calculation to make predictive statement of the product
| D - Demonstration | Demonstration | The requirement is verified by manipulating and examining the output product
| T - Test | Test | The requirement is verified by manipulating and measuring the output of the prodcut (if not measurable, it's a demonstration)
Validation platform | Development paltform | Development paltform | The test is meant to be executed on the development platform
| Integration platform | Integration platform | The test is meant to be executed on the integration platform
| Software proofing platform | Software proofing platform | The test is meant to be executed on the software proofing platform
| Cubicle factory | Cubicle factory | The test is meant to be executed in the cubicle factory
| On site | On site | The test is meant to be executed on site
How to customize Enumeration ?
Enumeration are store in "defaultValues" sheet.

## defaultValues (hidden)
Legend | Step state | Context | Regression | Writing Status | Running Status | TH/NTH | IADT | Validation platform | Version | System | Location | Type of test | Projects | Test stage
Do not modify | OK | X | Yes | not written | not run | TH | I - Inspection | Development paltform | V0 | AFC | HKB | Visual inspection | 1166B - SCL Phase 2 | Internal tests
Can be modify | OKWC | P | No | in progress | in progress | NTH | A - Analysis | Integration platform | V1 | AFC & SAMS | ADM | Demonstration test | 3733 - TKL | Software proofing tests
| NOK |  |  | written & reviewed OK | run completed |  | D - Demonstration | Software proofing platform | V2 | BMS | EXH | Communication test | 759 - WIL/KTE | Factory Acceptance tests
| NT | [5 empty] | T - Test | Cubicle factory | V3 | BS | SOV | Software unit test | 762 - WIL/KTE/SIL | Installation tests
| OS | [6 empty] | On site | V4 | CASS | NOV | Software integration test | 966 - SIL E | Site integration tests
[9 empty] | V5 | CDN | HUH | System integration test | DHLRT | Interface and integrated tests
[9 empty] | V6 | COM | EAP 7 | Point-to-point test | NWSL | System acceptance tests
[9 empty] | V7 | ERL PRC & BHT TVS | EAP 1-6 | End-to-end test |  | Test running
[9 empty] | V8 | FG | MKK | Functional test |  | Training System
[9 empty] | V9 | ITDN | KOT | Data applicable test |  | Other (e.g. Interfaces)
[9 empty] | V10 | LIF & ESC | TAW
[10 empty] | MCS | SHT
[10 empty] | MCS (CMCS_SMS) | HTD
[10 empty] | MCS (DBMS) | FOT
[10 empty] | MCS (DSS) | RAC
[10 empty] | MCS (E.Sign PLC) | UNI
[10 empty] | MCS (FEP) | TAD
[10 empty] | MCS (Field PLC) | TAP
[10 empty] | MCS (IBP) | TWO
[10 empty] | MCS (PRC PLC) | FAN
[10 empty] | MCS (SDS) | SHS
[10 empty] | MCS (TSS) | LOW
[10 empty] | MIMIC | CTV
[10 empty] | Misc | SSV
[10 empty] | MMIS | LMC
[10 empty] | OHL | OCC
PMW
POW
PSD & APG
RAD
RS
SIG
TECS
TETRA
TGMS
TODS
UITS
URL PRC

## Language (hidden)
En | Fr | Ch | Value
0
Language | Langue |  | Language
0
STD information | Information du STD |  | STD information
STD ID | ID du STD | 测试表格编号 | STD ID
Version of the test sheet | Version de la fiche de test |  | Version of the test sheet
Project | Projet |  | Project
Test type | Type de test |  | Test type
Test stage | Phase de test | 测试阶段 | Test stage
Stage category | Catégorie de la phase de test |  | Stage category
Verification method (IADT) | Méthode de vérification (IADT) |  | Verification method (IADT)
Resources required for test | Ressources nécéssaires pour le test |  | Resources required for test
Estimate preparation duration | Durée estimée de préparation |  | Estimate preparation duration
Estimate running duration | Durée estimée d'exécution |  | Estimate running duration
Test during TH/NTH | Test pendant TH/NTH |  | Test during TH/NTH
Number of tester(s) | Nombre de testeur(s) |  | Number of tester(s)
Equipment and quantity | Equipement et quantité |  | Equipment and quantity
Applicable location(s) | Localisation(s) applicable(s) |  | Applicable location(s)
Test title | Titre du Test | 测试标题 | Test title
Test objective | Objectif du test | 测试目的 | Test objective
0
Author information | Informations sur l'auteur |  | Author information
Written by | Rédacteur |  | Written by
Writter email | Adresse mail du rédacteur |  | Writter email
Writing status | Etat de l'écriture |  | Writing status
Writing date | Date d'écriture |  | Writing date
0
STD Checksum | Checksum du STD |  | STD Checksum
0
Covered requirements | Exigence couvertes |  | Covered requirements
0
STR information | Information du STR |  | STR information
System version under test | Version systeme testée | 软件版本 | System version under test
Test environment | Environnement de test |  | Test environment
IO schedule version | Version de l'IO list | I/O定义版本 | IO schedule version
Termination schedule version | Version du termination schedule |  | Termination schedule version
Allocated location(s) | Localisation(s) appliquée(s) |  | Allocated location(s)
Total steps | Total pas |  | Total steps
0
Tester information | Informations sur le testeur |  | Tester information
Run by | Testeur |  | Run by
Runner email | Adresse mail du testeur |  | Runner email
Running date | Date de l'exécution |  | Running date
Approximate preparation duration | Durée approximative de préparation |  | Approximate preparation duration
Approximate running duration | Durée approximative d'exécution |  | Approximate running duration
Instrument calibration certificate | Certificat de calibration des instruments |  | Instrument calibration certificate
0
STR results | Resultats du STR |  | STR results
Total Not Tested | Total pas restants |  | Total Not Tested
Total OK | Total OK |  | Total OK
Total OKWC | Total OKWC |  | Total OKWC
Total NOK | Total NOK |  | Total NOK
Total Not Testable | Total Non Testable |  | Total Not Testable
Total Out Of Scope | Total Hors Scope |  | Total Out Of Scope
Test case result | Resultat du cas de test | 测试结果 | Test case result
0
STR metrics | Métriques du STR |  | STR metrics
% Not Tested | % pas restants |  | % Not Tested
% OK | % OK |  | % OK
% OKWC | % OKWC |  | % OKWC
% NOK | % NOK |  | % NOK
% Not Testable | % Non Testable |  | % Not Testable
% Out Of Scope | % Hors Scope |  | % Out Of Scope
Number of test steps with defect | Nombre de pas de test avec défaut |  | Number of test steps with defect
0
Number of test cases | Nombre de cas de test |  | Number of test cases
Number of test cases for regression | Nombre de cas de test de non régression |  | Number of test cases for regression
Number of test cases in live session | Nombre de cas de test en "live session" |  | Number of test cases in live session
0
Last run date | Date de dernière exécution |  | Last run date
% OK | % OK |  | % OK
System version under test | Version systeme testée |  | System version under test
Software test environment | Environnement de test logiciel |  | Software test environment
Hardware test environment | Environnement de test matériel |  | Hardware test environment
0
To be filled from list | A remplir depuis une liste |  | To be filled from list
Automatically filled | Rempli automatiquement |  | Automatically filled
To let empty | A laisser vide |  | To let empty
Context step | Pas de contexte |  | Context step
To be filled by author | A remplir par l'auteur |  | To be filled by author
To be filled by tester | A remplir par le testeur |  | To be filled by tester
0
Test case description | Description du cas de test |  | Test case description
Regression | Non régression |  | Regression
Validation platform | Plateforme de validation |  | Validation platform
Tester name | Nom du testeur |  | Tester name
Last test date | Date de dernière execution |  | Last test date
0
Test case id | Identifiant du cas de test |  | Test case id
Context | Contexte |  | Context
Step # | Pas de test # |  | Step #
Step description | Description du pas de test | 输入/动作 | Step description
Expected result | Résultat attendu | 预期结果 | Expected result
Verification type | Type de vérification |  | Verification type
Last state date | Date de dernière exécution | 日期 | Last state date
Tester | Testeur | 测试人 | Tester
Result | Résultat |  | Result
Associated defect (PCR ID) | Défaut associé |  | Associated defect (PCR ID)
Comment on result | Commentaire sur le résultat |  | Comment on result
Historic defects | Défauts associés précédemment |  | Historic defects
Requirement | Exigence attachée |  | Requirement
Free column | Colonne libre |  | Free column
Test case result | Resultat du cas de test |  | Test case result
0
Passed | Passé |  | Passed
Failed | Manqué |  | Failed
Blocked | Bloqué |  | Blocked
Error | Erreur |  | Error
Inconclusive | Non concluant |  | Inconclusive
0
Test state | Etat du test |  | Test state
0
Legends | Légendes |  | Legends
0
Yes | Oui |  | Yes
No | Non |  | No
Comments | Commentaires | 意见 | Comments
Remedial work | Action corrective |  | Remedial work
Steps tested on last run date | Pas testés lors de dernière exécution |  | Steps tested on last run date
Associated defects | Défauts associés |  | Associated defects
Customer / External Signature | Client / Externe Signature |  | Customer / External Signature
Thales Signature | Thales Signature |  | Thales Signature
Instance of the test sheet execution | Instance d'éxécution |  | Instance of the test sheet execution
Test sheet Source | Source STD |  | Test sheet Source
Number of test steps OKWC or NOK without PCR | Total pas de tests NOK ou OKWC sans PCR |  | Number of test steps OKWC or NOK without PCR
Total requirements NOK | Total des exigences NOK |  | Total requirements NOK
Traceability | Tracabilité |  | Traceability
Controls on the inputs | Controles des données insérées |  | Controls on the inputs
Information | Information |  | Information
Number of test steps OS without comments | Total Hors Scope sans commentaire |  | Number of test steps OS without comments
Duration for STD preparation | Durée pour la préparation du STD |  | Duration for STD preparation
Requirement Source Version | Version des exigences |  | Requirement Source Version
0
Notes | Notes |  | Notes
0
Version of Orchestra format | Version du format Orchestra |  | Version of Orchestra format
0
0
0
0
0
0
0

## Automation (hidden)
Configuration to create Automation Script to a Word Document
Target
Directory
Template
Files for the import to create the script
ID | New File ? | New Name | File Source | Free Field 1 | Free Field 2 | Free Field 3 | Free Field 4 | Free Field 5
Import General Data
Source of Import |  |  |  |  | Word Target Document based on template selected
Data name | Type | Table Id or Value | Line | Column | Field name | Table ID | Line | Column

## Export (hidden)
Configuration to export to a Word Document
Target
Directory
Template
Files for the import
ID | New File ? | New Name | File Source | Free Field 1 | Free Field 2 | Free Field 3 | Free Field 4 | Free Field 5
end
end
end
end
end
end
end
end
end
end
Import General Data
Source of Import based on Orchestra template |  |  |  |  | Word Target Document based on template selected
Data name | Type | Table Id or Value | Line | Column | Field name | Table ID | Line | Column
Test sheet identification | Value from Excel | Summary | 3 | 5 | Test sheet identification | 1 | 1 | 2
Test sheet version | Value from Excel | Summary | 4 | 5 | Test sheet version | 1 | 1 | 3
Attendee | Value | 966 MCS, MTR | 24 | 8 | Attendee | 1 | 1 | 5
Test Title | Value from Excel | Summary | 9 | 5 | Test Title | 1 | 2 | 2
Purpose of the test | Value from Excel | Summary | 10 | 5 | Purpose of the test | 1 | 2 | 4
Test phase | Value from Excel | Summary | 6 | 5 | Test Phase | 2 | 1 | 2
Configuration | Value from Excel | Summary | 14 | 5 | Configuration | 2 | 1 | 4
Location of test | Value | TT&S HK Office |  |  | Location of test | 2 | 2 | 2
Instrument calibration date | Value |  |  |  | Instrument calibration date | 2 | 2 | 4
System version | Value from Excel | Summary | 13 | 5 | System version | 3 | 1 | 2
Test id | Value from Excel | Summary | 3 | 5 | Test id | 4 | 1 | 1
Test id | Value from Excel | Summary | 3 | 5 | Test id | 5 | 1 | 1
Import Steps
Source for import |  |  |  |  | Word Target Document based on template selected
Starting line | LatestRun | Starting line | 17 |  | Template Line | 4 | Starting line | 3
Data name | Type | Sheet Name, Table, value or formula | Starting Line | Column | Field name | Table ID | Starting Line | Column
Step Number | Value from Excel | LatestRun | 17 | 2 | Step Number | 4 | 3 | 1
Step description | Value from Excel | LatestRun | 17 | 3 | Step description | 4 | 3 | 2
Expected result | Value from Excel | LatestRun | 17 | 4 | Expected result | 4 | 3 | 3
Verification type | Not exported | LatestRun | 17 | 5 | Verification type | 4 | 3 | 0
OK | Value | [ ] | 17 | 6 | OK | 4 | 3 | 4
OKWC | Value | [ ] | 17 |  | OKWC | 4 | 3 | 6
NOK | Value | [ ] | 17 |  | NOK | 4 | 3 | 5
Associated defect | Value from Excel | LatestRun | 17 | 7 | PCR | 4 | 3 | 7
Comment | Value from Excel | LatestRun | 17 | 8 | Comment | 4 | 3 | 8
Export to Word

## Import (hidden)
Configuration to import data from a file to this Excel Test Sheet - Matrix of applicability
Target
Directory
Files for the import | [19 empty] | Log
|  |  |  | FreeField 1 | FreeField 2 | FreeField 3 | FreeField 4 | FreeField 5 | FreeField 6 | FreeField 7 | FreeField 8 | FreeField 9 | FreeField 10 | FreeField 11 | FreeField 12 | FreeField 13 | FreeField 14 | FreeField 15 | FreeField 16
ID | New File Name | File Location | Template | STD ID | Test title | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Not used | Start Update at : 14:45:37 | Nb Steps
Import General Data
Source for import |  |  |  |  | Target in Orchestra STD
Data name | Type | Sheet Name, Table, value or formula | Line | Column | Field name | Sheet Name | Line | Column
Category of test | Value from File Free Field | FreeField4 |  |  | Category of test | Summary | 7 | 5
Location | Value from File Free Field | FreeField5 |  |  | Location | Summary | 8 | 5
Regression thread | Value | No |  |  | Regression thread | Summary | 3 | 8
Cubicle ID | Value from File Free Field | FreeField1 |  |  | Instance of the test sheet execution | Summary | 23 | 8
Cubicle ID | Value from File Free Field | FreeField1 |  |  | Cubicle ID | Summary | 19 | 5
System | Value | System |  |  | System Label | Summary | 19 | 7
System | Value from File Free Field | FreeField3 |  |  | System | Summary | 19 | 8
Room | Value | Room |  |  | Label Room | Summary | 20 | 7
Room | Value from File Free Field | FreeField6 |  |  | Room | Summary | 20 | 8
Import Steps
Source for import |  |  |  |  | Target in Orchestra STD
Data name | Type | Sheet Name, Table, value or formula | Starting Line | Column | Field name | Sheet Name | Starting Line | Column
Generate STD

## ToolVersion (hidden)
Version | Date | Responsible | Comments
v01 | - | Group Thales | Version 4.2.1 From Orchestra
v02 | 2014-02-12 | D. Castilla
v03 |  | D. Castilla
v04 |  | D. Castilla
v05 |  | D. Castilla
v06 | 2014-02-19 | D. Castilla | Clean the VBA code
v07 | 2014-02-20 | D. Castilla | Clean the VBA code
v08 | 2014-02-21 | D. Castilla | Clean the VBA code
v09 | 2014-02-22 | D. Castilla | Clean the VBA code
v10 | 2014-04-06 | D. Castilla | Improve the Summary organization
v11 | 2014-04-12 | D. Castilla | Optimize the function Import to be able to link each file with a specific template. + Add legend in the summary to explain the Stat of result
v12
v13
v14 | 2014-07-19 | D. Castilla & J. Ng | Export function from Excel to Word Add Duration for Preparation Field
v15 | 2014-07-29 | D. Castilla & J. Ng | Add Requirement Version in the Summary Sheet
v16 | 2016-02-05 | D. Castilla & C. Rousseau | - Add ProcedureVersion sheet to track the changes in the content of the STD (the field Test case version is now automatically computed based on the content of this tab) - Delete Project Compliance sheet - Reworked summary (add/removed fields, added color to differenciate to be filled by author/tester) - Reworked language (re-order to match order in summary sheet) - Reworked User manual (remove images, re-wrote the meaning of enumerations, etc.)
v17 | 2016-02-17 | C. Rousseau | - Add Result Matrix sheet - Reworked summary - Add chinese language - Add checksum functionality
v18 | 2016-03-29 | C. Rousseau | Updated the formula in the tab Language, such that Excel will not ask anymore to save the file on closure when the file has not been modified
v19 | 2016-03-31 | C. Rousseau | Add back the Test Category
v20 | 2016-05-31 | C. Rousseau | - Updated the format to have a better contrast for B&W printing - Updated the Import function to support up to 16 free fields

## ProcedureVersion (hidden)
Version | Date | Responsible | Comments
v01 | 2016-07-04 | Peter CHAN | Creation

## Result Matrix (hidden)
Steps
|  | Total Out Of Scope | Total OK | Total OKWC | Total NOK | Total Not Tested | Total Not Testable
Cases | NT | allowed | 0 | 0 | 0 | 100% | 0
| OS | 100% | 0 | 0 | 0 | 0 | 0
| Incomplete | allowed | at least 1 |  | 0 | at least 1
| NTestable | allowed | 0 | 0 | 0 | 0 | 100%
| NOK | allowed | allowed | allowed | at least 1 | allowed | allowed
| OKWC | allowed | allowed | at least 1 | 0 | 0 | 0
| OK | allowed | 100% | 0 | 0 | 0 | 0

## Report
Station | Eqpt_Code | Eqpt_Description(MCS) | Eqpt_Identifier | Attribute_Description(MCS) | DC_Data_Type | v0_label(1) | v0_Severity | v0_State | v1_label(2) | v1_Severity | v1_State | Register_Address/File | Bit_offset | Result | Associated defect (PCR ID) | Comment on result | System version under test | Date | Tester
G01_ | CMDS | &DB_EQPT_CMDS | G01-BMS-CMDS-01 | &DB_ATTR_CMDS_PT1 | DI | OCC | 0 | N | STATION | 0 | N | 0 | 0 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | PA1_ | &DB_EQPT_PA1_ | G01-PA1 | &DB_ATTR_PA1__PT1 | DI | CLOSE | 0 | N | No CLOSE | 0 | N | 1 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | PA1_ | &DB_EQPT_PA1_ | G01-PA1 | &DB_ATTR_PA1__PT2 | DI | OPEN | 0 | N | No OPEN | 0 | N | 1 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | PA1_ | &DB_EQPT_PA1_ | G01-PA1 | &DB_ATTR_PA1__PT3 | DI | TRIP | 1 | A | No TRIP | 0 | N | 1 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | PA1_ | &DB_EQPT_PA1_ | G01-PA1 | &DB_ATTR_PA1__PT4 | DI | NORMAL | 0 | N | ALARM | 1 | A | 1 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | PA2_ | &DB_EQPT_PA2_ | PA5-1 | &DB_ATTR_PA2__PT3 | DI | CLOSE | 0 | N | No CLOSE | 0 | N | 1 | 5 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | PA2_ | &DB_EQPT_PA2_ | PA5-1 | &DB_ATTR_PA2__PT4 | DI | OPEN | 0 | N | No OPEN | 0 | N | 1 | 6 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-A | &DB_ATTR_ECP__PT1 | DI | CLOSE | 0 | N | No CLOSE | 0 | N | 2 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-A | &DB_ATTR_ECP__PT2 | DI | OPEN | 0 | N | No OPEN | 0 | N | 2 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-A | &DB_ATTR_ECP__PT3 | DI | TRIP | 1 | A | No TRIP | 0 | N | 2 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-A | &DB_ATTR_ECP__PT4 | DI | NORMAL | 0 | N | ALARM | 1 | A | 2 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-B | &DB_ATTR_ECP__PT1 | DI | CLOSE | 0 | N | No CLOSE | 0 | N | 3 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-B | &DB_ATTR_ECP__PT2 | DI | OPEN | 0 | N | No OPEN | 0 | N | 3 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-B | &DB_ATTR_ECP__PT3 | DI | TRIP | 1 | A | No TRIP | 0 | N | 3 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | ECP_ | &DB_EQPT_ECP_ | ECP-B | &DB_ATTR_ECP__PT4 | DI | NORMAL | 0 | N | ALARM | 1 | A | 3 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | GCP_ | &DB_EQPT_GCP_ | GCP | &DB_ATTR_GCP__PT1 | DI | CLOSE | 0 | N | No CLOSE | 0 | N | 4 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | GCP_ | &DB_EQPT_GCP_ | GCP | &DB_ATTR_GCP__PT2 | DI | OPEN | 0 | N | No OPEN | 0 | N | 4 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | GCP_ | &DB_EQPT_GCP_ | GCP | &DB_ATTR_GCP__PT3 | DI | TRIP | 1 | A | No TRIP | 0 | N | 4 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | GCP_ | &DB_EQPT_GCP_ | GCP | &DB_ATTR_GCP__PT4 | DI | ON | 1 | A | OFF | 0 | N | 4 | 5 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | GCP_ | &DB_EQPT_GCP_ | GCP | &DB_ATTR_GCP__PT29 | DI | ALARM | 1 | A | NORMAL | 0 | N | 4 | 6 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | GCP_ | &DB_EQPT_GCP_ | GCP | &DB_ATTR_GCP__PT5 | DI | NORMAL | 0 | N | ALARM | 1 | A | 4 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT1 | DI | RUNNING | 0 | N | STOPPED | 0 | N | 10 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT2 | DI | ALARM | 1 | A | NORMAL | 0 | N | 10 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT3 | DI | ALARM | 1 | A | NORMAL | 0 | N | 10 | 6 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT4 | DI | ON | 0 | N | OFF | 1 | A | 10 | 7 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT5 | DI | ALARM | 1 | A | NORMAL | 0 | N | 10 | 11 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT6 | DI | REMOTE | 0 | N | No REMOTE | 0 | N | 10 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT7 | DI | OFF | 0 | N | No OFF | 0 | N | 10 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT8 | DI | LOCAL | 0 | N | No LOCAL | 0 | N | 10 | 5 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G101 | &DB_ATTR_EAF1_PT9 | DI | AUTO | 0 | N | MANUAL | 0 | N | 10 | 0 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT1 | DI | RUNNING | 0 | N | STOPPED | 0 | N | 11 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT2 | DI | ALARM | 1 | A | NORMAL | 0 | N | 11 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT3 | DI | ALARM | 1 | A | NORMAL | 0 | N | 11 | 6 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT4 | DI | ON | 0 | N | OFF | 1 | A | 11 | 7 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT5 | DI | REMOTE | 0 | N | No REMOTE | 0 | N | 11 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT6 | DI | OFF | 0 | N | No OFF | 0 | N | 11 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT7 | DI | LOCAL | 0 | N | No LOCAL | 0 | N | 11 | 5 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G102 | &DB_ATTR_EAF__PT10 | DI | AUTO | 0 | N | MANUAL | 0 | N | 11 | 0 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT1 | DI | RUNNING | 0 | N | STOPPED | 0 | N | 12 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT2 | DI | ALARM | 1 | A | NORMAL | 0 | N | 12 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT3 | DI | ALARM | 1 | A | NORMAL | 0 | N | 12 | 6 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT4 | DI | ON | 0 | N | OFF | 1 | A | 12 | 7 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT5 | DI | REMOTE | 0 | N | No REMOTE | 0 | N | 12 | 3 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT6 | DI | OFF | 0 | N | No OFF | 0 | N | 12 | 4 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT7 | DI | LOCAL | 0 | N | No LOCAL | 0 | N | 12 | 5 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF_ | &DB_EQPT_EAF_ | G01-EAF-G103 | &DB_ATTR_EAF__PT10 | DI | AUTO | 0 | N | MANUAL | 0 | N | 12 | 0 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G104 | &DB_ATTR_EAF1_PT1 | DI | RUNNING | 0 | N | STOPPED | 0 | N | 13 | 1 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G104 | &DB_ATTR_EAF1_PT2 | DI | ALARM | 1 | A | NORMAL | 0 | N | 13 | 2 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G104 | &DB_ATTR_EAF1_PT3 | DI | ALARM | 1 | A | NORMAL | 0 | N | 13 | 6 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
OK
G01_ | EAF1 | &DB_EQPT_EAF1 | G01-EAF-G104 | &DB_ATTR_EAF1_PT4 | DI | ON | 0 | N | OFF | 1 | A | 13 | 7 | NOK |  | Link to Raw Result |  | 2019-06-26 | TAT
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK

## Raw Result
Overall Result | EventList Result | Data Type | Register | Register Offset | Triggering State | Station |  | EQP Code |  | EQP Number |  | EQP Description |  | Attribute Description |  | State |  | Alarm Severity |  | Check Number of Event
[6 empty] | Searched | Found | Searched | Found | Searched | Found | Searched | Found | Searched | Found | Searched | Found | Searched | Found
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 0 | 0 | 0 | G01_ | G01_ | CMDS | MBT2 | G01-BMS-CMDS-01 | G01__BMSMBT_ | &DB_EQPT_CMDS | &DB_EQPT_MBT2 | &DB_ATTR_CMDS_PT1 | &DB_ATTR_MBT2_PT5 | OCC | &DB_BIT_MBT2_PT5_V3 | 0.0 | 0.0
| NOK | DI | 0 | 0 | 1 | G01_ | G01_ | CMDS | MBT2 | G01-BMS-CMDS-01 | G01__BMSMBT_ | &DB_EQPT_CMDS | &DB_EQPT_MBT2 | &DB_ATTR_CMDS_PT1 | &DB_ATTR_MBT2_PT5 | STATION | &DB_BIT_MBT2_PT5_V3 | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 1 | 1 | 0 | G01_ | G01_ | PA1_ | CMDS | G01-PA1 | G01-BMS-CMDS-01 | &DB_EQPT_PA1_ | &DB_EQPT_CMDS | &DB_ATTR_PA1__PT1 | &DB_ATTR_CMDS_PT2 | CLOSE | STATION | 0.0 | 0.0
| NOK | DI | 1 | 1 | 1 | G01_ | G01_ | PA1_ | CMDS | G01-PA1 | G01-BMS-CMDS-01 | &DB_EQPT_PA1_ | &DB_EQPT_CMDS | &DB_ATTR_PA1__PT1 | &DB_ATTR_CMDS_PT2 | No CLOSE | STATION | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 1 | 2 | 0 | G01_ | G01_ | PA1_ | EAF_ | G01-PA1 | G01-EAF-G102 | &DB_EQPT_PA1_ | &DB_EQPT_EAF_ | &DB_ATTR_PA1__PT2 | &DB_ATTR_EAF__PT11 | OPEN | MANUAL | 0.0 | 0.0
| NOK | DI | 1 | 2 | 1 | G01_ | G01_ | PA1_ | EAF_ | G01-PA1 | G01-EAF-G102 | &DB_EQPT_PA1_ | &DB_EQPT_EAF_ | &DB_ATTR_PA1__PT2 | &DB_ATTR_EAF__PT11 | No OPEN | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 1 | 3 | 0 | G01_ | G01_ | PA1_ | EAF_ | G01-PA1 | G01-EAF-G102 | &DB_EQPT_PA1_ | &DB_EQPT_EAF_ | &DB_ATTR_PA1__PT3 | &DB_ATTR_EAF__PT8 | TRIP |  | 1.0 | 0.0
| NOK | DI | 1 | 3 | 1 | G01_ | G01_ | PA1_ | EAF_ | G01-PA1 | G01-EAF-G102 | &DB_EQPT_PA1_ | &DB_EQPT_EAF_ | &DB_ATTR_PA1__PT3 | &DB_ATTR_EAF__PT8 | No TRIP |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 1 | 4 | 0 | G01_ | G01_ | PA1_ | EAF_ | G01-PA1 | G01-EAF-G102 | &DB_EQPT_PA1_ | &DB_EQPT_EAF_ | &DB_ATTR_PA1__PT4 | &DB_ATTR_EAF__PT9 | NORMAL |  | 0.0 | 0.0
| NOK | DI | 1 | 4 | 1 | G01_ | G01_ | PA1_ | EAF_ | G01-PA1 | G01-EAF-G102 | &DB_EQPT_PA1_ | &DB_EQPT_EAF_ | &DB_ATTR_PA1__PT4 | &DB_ATTR_EAF__PT9 | ALARM |  | 1.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 1 | 5 | 0 | G01_ | G01_ | PA2_ | EAF_ | PA5-1 | G01-EAF-G103 | &DB_EQPT_PA2_ | &DB_EQPT_EAF_ | &DB_ATTR_PA2__PT3 | &DB_ATTR_EAF__PT11 | CLOSE | MANUAL | 0.0 | 0.0
| NOK | DI | 1 | 5 | 1 | G01_ | G01_ | PA2_ | EAF_ | PA5-1 | G01-EAF-G103 | &DB_EQPT_PA2_ | &DB_EQPT_EAF_ | &DB_ATTR_PA2__PT3 | &DB_ATTR_EAF__PT11 | No CLOSE | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 1 | 6 | 0 | G01_ | G01_ | PA2_ | EAF_ | PA5-1 | G01-EAF-G103 | &DB_EQPT_PA2_ | &DB_EQPT_EAF_ | &DB_ATTR_PA2__PT4 | &DB_ATTR_EAF__PT8 | OPEN |  | 0.0 | 0.0
| NOK | DI | 1 | 6 | 1 | G01_ | G01_ | PA2_ | EAF_ | PA5-1 | G01-EAF-G103 | &DB_EQPT_PA2_ | &DB_EQPT_EAF_ | &DB_ATTR_PA2__PT4 | &DB_ATTR_EAF__PT8 | No OPEN |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 2 | 1 | 0 | G01_ | G01_ | ECP_ | EAF_ | ECP-A | G01-EAF-G103 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT1 | &DB_ATTR_EAF__PT9 | CLOSE |  | 0.0 | 0.0
| NOK | DI | 2 | 1 | 1 | G01_ | G01_ | ECP_ | EAF_ | ECP-A | G01-EAF-G103 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT1 | &DB_ATTR_EAF__PT9 | No CLOSE |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 2 | 2 | 0 | G01_ | G01_ | ECP_ | EAF1 | ECP-A | G01-EAF-G104 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT2 | &DB_ATTR_EAF1_PT10 | OPEN | MANUAL | 0.0 | 0.0
| NOK | DI | 2 | 2 | 1 | G01_ | G01_ | ECP_ | EAF1 | ECP-A | G01-EAF-G104 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT2 | &DB_ATTR_EAF1_PT10 | No OPEN | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 2 | 3 | 0 | G01_ | G01_ | ECP_ | EAF1 | ECP-A | G01-EAF-G104 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT3 | &DB_ATTR_EAF1_PT11 | TRIP |  | 1.0 | 0.0
| NOK | DI | 2 | 3 | 1 | G01_ | G01_ | ECP_ | EAF1 | ECP-A | G01-EAF-G104 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT3 | &DB_ATTR_EAF1_PT11 | No TRIP |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 2 | 4 | 0 | G01_ | G01_ | ECP_ | EAF1 | ECP-A | G01-EAF-G104 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT4 | &DB_ATTR_EAF1_PT12 | NORMAL |  | 0.0 | 0.0
| NOK | DI | 2 | 4 | 1 | G01_ | G01_ | ECP_ | EAF1 | ECP-A | G01-EAF-G104 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT4 | &DB_ATTR_EAF1_PT12 | ALARM |  | 1.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 3 | 1 | 0 | G01_ | G01_ | ECP_ | EAF_ | ECP-B | G01-EAF-G105 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT1 | &DB_ATTR_EAF__PT11 | CLOSE | MANUAL | 0.0 | 0.0
| NOK | DI | 3 | 1 | 1 | G01_ | G01_ | ECP_ | EAF_ | ECP-B | G01-EAF-G105 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT1 | &DB_ATTR_EAF__PT11 | No CLOSE | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 3 | 2 | 0 | G01_ | G01_ | ECP_ | EAF_ | ECP-B | G01-EAF-G105 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT2 | &DB_ATTR_EAF__PT8 | OPEN |  | 0.0 | 0.0
| NOK | DI | 3 | 2 | 1 | G01_ | G01_ | ECP_ | EAF_ | ECP-B | G01-EAF-G105 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT2 | &DB_ATTR_EAF__PT8 | No OPEN |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 3 | 3 | 0 | G01_ | G01_ | ECP_ | EAF_ | ECP-B | G01-EAF-G105 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT3 | &DB_ATTR_EAF__PT9 | TRIP |  | 1.0 | 0.0
| NOK | DI | 3 | 3 | 1 | G01_ | G01_ | ECP_ | EAF_ | ECP-B | G01-EAF-G105 | &DB_EQPT_ECP_ | &DB_EQPT_EAF_ | &DB_ATTR_ECP__PT3 | &DB_ATTR_EAF__PT9 | No TRIP |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 3 | 4 | 0 | G01_ | G01_ | ECP_ | EAF1 | ECP-B | G01-EAF-G106 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT4 | &DB_ATTR_EAF1_PT10 | NORMAL | MANUAL | 0.0 | 0.0
| NOK | DI | 3 | 4 | 1 | G01_ | G01_ | ECP_ | EAF1 | ECP-B | G01-EAF-G106 | &DB_EQPT_ECP_ | &DB_EQPT_EAF1 | &DB_ATTR_ECP__PT4 | &DB_ATTR_EAF1_PT10 | ALARM | MANUAL | 1.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 4 | 1 | 0 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G106 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT1 | &DB_ATTR_EAF1_PT11 | CLOSE |  | 0.0 | 0.0
| NOK | DI | 4 | 1 | 1 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G106 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT1 | &DB_ATTR_EAF1_PT11 | No CLOSE |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 4 | 2 | 0 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G106 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT2 | &DB_ATTR_EAF1_PT12 | OPEN |  | 0.0 | 0.0
| NOK | DI | 4 | 2 | 1 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G106 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT2 | &DB_ATTR_EAF1_PT12 | No OPEN |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 4 | 3 | 0 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G107 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT3 | &DB_ATTR_EAF1_PT10 | TRIP | MANUAL | 1.0 | 0.0
| NOK | DI | 4 | 3 | 1 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G107 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT3 | &DB_ATTR_EAF1_PT10 | No TRIP | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 4 | 5 | 0 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G107 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT4 | &DB_ATTR_EAF1_PT11 | ON |  | 1.0 | 0.0
| NOK | DI | 4 | 5 | 1 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G107 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT4 | &DB_ATTR_EAF1_PT11 | OFF |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 4 | 6 | 0 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G107 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT29 | &DB_ATTR_EAF1_PT12 | ALARM |  | 1.0 | 0.0
| NOK | DI | 4 | 6 | 1 | G01_ | G01_ | GCP_ | EAF1 | GCP | G01-EAF-G107 | &DB_EQPT_GCP_ | &DB_EQPT_EAF1 | &DB_ATTR_GCP__PT29 | &DB_ATTR_EAF1_PT12 | NORMAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 4 | 4 | 0 | G01_ | G01_ | GCP_ | SAC1 | GCP | G01-SAC-G112A | &DB_EQPT_GCP_ | &DB_EQPT_SAC1 | &DB_ATTR_GCP__PT5 | &DB_ATTR_SAC1_PT9 | NORMAL | MANUAL | 0.0 | 0.0
| NOK | DI | 4 | 4 | 1 | G01_ | G01_ | GCP_ | SAC1 | GCP | G01-SAC-G112A | &DB_EQPT_GCP_ | &DB_EQPT_SAC1 | &DB_ATTR_GCP__PT5 | &DB_ATTR_SAC1_PT9 | ALARM | MANUAL | 1.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 1 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G112A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT1 | &DB_ATTR_SAC1_PT6 | RUNNING |  | 0.0 | 0.0
| NOK | DI | 10 | 1 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G112A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT1 | &DB_ATTR_SAC1_PT6 | STOPPED |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 2 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G112A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT2 | &DB_ATTR_SAC1_PT7 | ALARM |  | 1.0 | 0.0
| NOK | DI | 10 | 2 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G112A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT2 | &DB_ATTR_SAC1_PT7 | NORMAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 6 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G113A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT3 | &DB_ATTR_SAC1_PT9 | ALARM | MANUAL | 1.0 | 0.0
| NOK | DI | 10 | 6 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G113A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT3 | &DB_ATTR_SAC1_PT9 | NORMAL | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 7 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G113A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT4 | &DB_ATTR_SAC1_PT6 | ON |  | 0.0 | 0.0
| NOK | DI | 10 | 7 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G113A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT4 | &DB_ATTR_SAC1_PT6 | OFF |  | 1.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 11 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G113A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT5 | &DB_ATTR_SAC1_PT7 | ALARM |  | 1.0 | 0.0
| NOK | DI | 10 | 11 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G113A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT5 | &DB_ATTR_SAC1_PT7 | NORMAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 3 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G101A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT6 | &DB_ATTR_SAC1_PT9 | REMOTE | MANUAL | 0.0 | 0.0
| NOK | DI | 10 | 3 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G101A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT6 | &DB_ATTR_SAC1_PT9 | No REMOTE | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 4 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G101A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT7 | &DB_ATTR_SAC1_PT6 | OFF |  | 0.0 | 0.0
| NOK | DI | 10 | 4 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G101A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT7 | &DB_ATTR_SAC1_PT6 | No OFF |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 5 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G101A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT8 | &DB_ATTR_SAC1_PT7 | LOCAL |  | 0.0 | 0.0
| NOK | DI | 10 | 5 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G101A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT8 | &DB_ATTR_SAC1_PT7 | No LOCAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 10 | 0 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G102A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT9 | &DB_ATTR_SAC1_PT9 | AUTO | MANUAL | 0.0 | 0.0
| NOK | DI | 10 | 0 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G101 | G01-SAC-G102A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT9 | &DB_ATTR_SAC1_PT9 | MANUAL | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 1 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G102 | G01-SAC-G102A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT1 | &DB_ATTR_SAC1_PT6 | RUNNING |  | 0.0 | 0.0
| NOK | DI | 11 | 1 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G102 | G01-SAC-G102A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT1 | &DB_ATTR_SAC1_PT6 | STOPPED |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 2 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G102 | G01-SAC-G102A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT2 | &DB_ATTR_SAC1_PT7 | ALARM |  | 1.0 | 0.0
| NOK | DI | 11 | 2 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G102 | G01-SAC-G102A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT2 | &DB_ATTR_SAC1_PT7 | NORMAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 6 | 0 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT3 | &DB_ATTR_VRV__PT7 | ALARM | MANUAL | 1.0 | 0.0
| NOK | DI | 11 | 6 | 1 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT3 | &DB_ATTR_VRV__PT7 | NORMAL | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 7 | 0 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT4 | &DB_ATTR_VRV__PT8 | ON |  | 0.0 | 0.0
| NOK | DI | 11 | 7 | 1 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT4 | &DB_ATTR_VRV__PT8 | OFF |  | 1.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 3 | 0 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT5 | &DB_ATTR_VRV__PT9 | REMOTE |  | 0.0 | 0.0
| NOK | DI | 11 | 3 | 1 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT5 | &DB_ATTR_VRV__PT9 | No REMOTE |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 4 | 0 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT6 | &DB_ATTR_VRV__PT23 | OFF |  | 0.0 | 0.0
| NOK | DI | 11 | 4 | 1 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT6 | &DB_ATTR_VRV__PT23 | No OFF |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 5 | 0 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT7 | &DB_ATTR_VRV__PT24 | LOCAL |  | 0.0 | 0.0
| NOK | DI | 11 | 5 | 1 | G01_ | G01_ | EAF_ | VRV_ | G01-EAF-G102 | G01-VRV-G101B | &DB_EQPT_EAF_ | &DB_EQPT_VRV_ | &DB_ATTR_EAF__PT7 | &DB_ATTR_VRV__PT24 | No LOCAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 11 | 0 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G102 | G01-SAC-G108A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT10 | &DB_ATTR_SAC1_PT9 | AUTO | MANUAL | 0.0 | 0.0
| NOK | DI | 11 | 0 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G102 | G01-SAC-G108A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT10 | &DB_ATTR_SAC1_PT9 | MANUAL | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 1 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G108A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT1 | &DB_ATTR_SAC1_PT6 | RUNNING |  | 0.0 | 0.0
| NOK | DI | 12 | 1 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G108A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT1 | &DB_ATTR_SAC1_PT6 | STOPPED |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 2 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G108A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT2 | &DB_ATTR_SAC1_PT7 | ALARM |  | 1.0 | 0.0
| NOK | DI | 12 | 2 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G108A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT2 | &DB_ATTR_SAC1_PT7 | NORMAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 6 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G109A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT3 | &DB_ATTR_SAC1_PT9 | ALARM | MANUAL | 1.0 | 0.0
| NOK | DI | 12 | 6 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G109A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT3 | &DB_ATTR_SAC1_PT9 | NORMAL | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 7 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G109A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT4 | &DB_ATTR_SAC1_PT6 | ON |  | 0.0 | 0.0
| NOK | DI | 12 | 7 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G109A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT4 | &DB_ATTR_SAC1_PT6 | OFF |  | 1.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 3 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G109A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT5 | &DB_ATTR_SAC1_PT7 | REMOTE |  | 0.0 | 0.0
| NOK | DI | 12 | 3 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G109A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT5 | &DB_ATTR_SAC1_PT7 | No REMOTE |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 4 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G110A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT6 | &DB_ATTR_SAC1_PT9 | OFF | MANUAL | 0.0 | 0.0
| NOK | DI | 12 | 4 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G110A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT6 | &DB_ATTR_SAC1_PT9 | No OFF | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 5 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G110A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT7 | &DB_ATTR_SAC1_PT6 | LOCAL |  | 0.0 | 0.0
| NOK | DI | 12 | 5 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G110A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT7 | &DB_ATTR_SAC1_PT6 | No LOCAL |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 12 | 0 | 0 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G110A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT10 | &DB_ATTR_SAC1_PT7 | AUTO |  | 0.0 | 0.0
| NOK | DI | 12 | 0 | 1 | G01_ | G01_ | EAF_ | SAC1 | G01-EAF-G103 | G01-SAC-G110A | &DB_EQPT_EAF_ | &DB_EQPT_SAC1 | &DB_ATTR_EAF__PT10 | &DB_ATTR_SAC1_PT7 | MANUAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 13 | 1 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G104 | G01-SAC-G111A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT1 | &DB_ATTR_SAC1_PT9 | RUNNING | MANUAL | 0.0 | 0.0
| NOK | DI | 13 | 1 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G104 | G01-SAC-G111A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT1 | &DB_ATTR_SAC1_PT9 | STOPPED | MANUAL | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 13 | 2 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G104 | G01-SAC-G111A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT2 | &DB_ATTR_SAC1_PT6 | ALARM |  | 1.0 | 0.0
| NOK | DI | 13 | 2 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G104 | G01-SAC-G111A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT2 | &DB_ATTR_SAC1_PT6 | NORMAL |  | 0.0 | 0.0
NOK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 13 | 6 | 0 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G104 | G01-SAC-G111A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT3 | &DB_ATTR_SAC1_PT7 | ALARM |  | 1.0 | 0.0
| NOK | DI | 13 | 6 | 1 | G01_ | G01_ | EAF1 | SAC1 | G01-EAF-G104 | G01-SAC-G111A | &DB_EQPT_EAF1 | &DB_EQPT_SAC1 | &DB_ATTR_EAF1_PT3 | &DB_ATTR_SAC1_PT7 | NORMAL |  | 0.0 | 0.0
OK
NOK | [19 empty] | Several events generated per trigger
| NOK | DI | 13 | 7 | 0 | G01_ | G01_ | EAF1 | VRV_ | G01-EAF-G104 | G01-VRV-G101C | &DB_EQPT_EAF1 | &DB_EQPT_VRV_ | &DB_ATTR_EAF1_PT4 | &DB_ATTR_VRV__PT7 | ON | MANUAL | 0.0 | 0.0
| NOK | DI | 13 | 7 | 1 | G01_ | G01_ | EAF1 | VRV_ | G01-EAF-G104 | G01-VRV-G101C | &DB_EQPT_EAF1 | &DB_EQPT_VRV_ | &DB_ATTR_EAF1_PT4 | &DB_ATTR_VRV__PT7 | OFF | MANUAL | 1.0 | 0.0
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
OK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK
NOK